2023-2024

# AL MAWAKEB AL GARHOUD

# DSIB ACTION PLAN

| Key Area 1: Ensure that all teachers make full use of assessment data to provide appropriately focused support and challenge for all students |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key Actions | Lead Person | Resources/ Cost | Timeline | Success Criteria | Progress |
| - Refine the assessment framework to promote collaboration among teachers to develop rigorous on-going and summative assessments. | - SC - Teachers | - Department Meeting - Assessments - Assessment Framework | - May 2023-June 2024 | - In phase 2, at least 75% of students meet the curriculum expectations in MAP (Spring 2024) and at least 50% of students exceed the curriculum expectations in MAP (Spring 2024). - In phases 3 and 4, at least 75% of students meet the curriculum expectations in MAP (Spring 2024) and at least 61% of students exceed the curriculum expectations in MAP (Spring 2024). |  |
| - Provide teachers with guidelines and models on using assessment data to inform instructions and accommodate to students’ learning needs. | - SC - Teachers | - Department Meeting - Internal Assessment results - Student Profile - MAP, CAT4, & NGRT reports | - November 2022-June 2024 | - In phase 2, at least 75% of students meet the curriculum expectations in MAP (Spring 2024) and at least 50% of students exceed the curriculum expectations in MAP (Spring 2024). - In phases 3 and 4, at least 75% of students meet the curriculum expectations in MAP (Spring 2024) and at least 61% of students exceed the curriculum expectations in MAP (Spring 2024). - In phases 2-4, at least 75% of students show progress in NGRT from Fall 2023 -Spring 2024. - 100% of the teachers can read and analyze data to inform instructions and accommodate to students’ learning needs. |  |
| - Develop rigorous annual professional development for leadership and teachers to build on the principles of assessment when reviewing and modifying the curriculum. | - SC - Teachers | - LMS academic resources - Scope & Sequence - Students’ data from internal & external assessments - Curriculum review guidelines | - June 2023 - June 2024 | - All Subject Coordinators implement successfully targeted department goals focusing on assessment data to review and modify the curriculum to meet all students’ needs. |  |
| - Provide professional development training for teachers to: - Evaluate what rigor is by collaboratively or/and independently designing and creating ongoing rigorous assessment and independent tasks aligned with the curriculum standards. | - SCs - Teachers | - Student Profiles - Class Rosters - CAT4 Reports - MAP Reports - NGRT Reports | - Sept. 2022-June 2024 | - All teachers effectively use data from all internal and external assessment sources to identify students’ areas of strengths and areas for development and to meet all students’ learning needs. |  |
| - Follow a systematic data literacy process to collect, read, analyze, and interpret data from internal and external (MAP, CAT4, NGRT, IBT) assessments: - Identify GAT, very abled, and students with very low verbal deficit. - Follow data analysis with high quality corrective instruction. - Reassess to demonstrate success and determine the effectiveness of the corrective instruction. | - SCs - Teachers | - CAT 4 reports - MAP reports - NGRT reports - IBT reports - Internal assessment Data - Student profile | - Sept. 2022-June 2024 | - At least 75% of teachers plan remediation/intervention sessions based on the analyzed data. - Students who are reassessed after corrective instruction show progress. |  |
| - Teachers train students to: - Read and interpret their external assessment results (MAP, NGRT, IBT) - Set their goals to show progress in the next external assessment window. - Practice on the skills set in their goal setting using IXL Skill Plan for Math, English, and Science - Reflect on teachers’ feedback given to them on the work done based on the goal setting. | - Teachers - Students | - MAP class reports - NGRT reports - IBT reports - Goal setting template - IXL skill plan | - Sept. 2023- May 2024 | - All students are aware of strengths and areas for development based on their external assessment results. - Most students set their next steps to improve their learning. |  |

| Key Area 2: Ensure that there is an appropriately led and sustained drive to improve literacy in all phases |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key Actions | Lead Person | Resources/ Cost | Timeline | Success Criteria | Progress |
| - Develop a sustained plan to promote literacy across phases by: - Ensuring access to a wide range of digital and non-digital reading material (RAZ and supplementary books). - Providing opportunities to engage with complex literary and informational texts. - Providing explicit instructions in reading strategies. - Providing ample opportunities to engage in writings that enhance critical thinking and analysis skills. - Promoting literacy activities such as read aloud, storytelling, and DEAR. - Engaging all stakeholders, including parents in supporting literacy instruction and student achievement. - In Arabic: participating in national competitions (Emirates Festival of Literature, Poetry for All and Chevron’s Readers Cup- Reading Arab Challenge) - Scheduling frequent library visits to develop reading habits. - Adding ‘Kutubee Platform” to enhance reading skills. - Creating ‘Reading Essentials” on school portal to promote “read aloud”. - Conducting Benchmark Exam –IBT to enhance reading skills. | - SC - Teachers | - RAZ platform - Library/ Supplementary books - ‘Kutubee” Platform - Circulars | - Oct. 2023- June 2024 | - All students are reading complex texts and writing extended pieces. - In phases 2-4, at least 75% of students show progress in NGRT from Fall 2023 -Spring 2024. |  |
| - In phase 2, build on and refine the Daily 4 framework that instills independent reading behaviors and skills among learners. | - SC - Teachers | - Class observations - PD schedule - Lesson plans - Running records | - Sept.2023-June 2024 | - In MAP Reading interim assessments, at least 61% of Gr.3-4 students show progress in reading level from Spring 2023-Spring 2024. - In NGRT at least 61% of Gr.1-4 students show progress in reading literacy skills from Fall 2023-Spring 2024. |  |
| - Provide opportunities for professional development on reading strategies. - Introduce reading routines based on the Science of Reading | - SC - Teachers | - PD Schedule - PD presentations - Reading Routines | - Sept. 2023-June 2024 | - All students are actively engaged in reading and writing. - In MAP Reading interim assessments, at least 61% of Gr.3-4 students show progress in reading level from Spring 2023-Spring 2024. - In NGRT at least 61% of Gr.1-4 students show progress in reading literacy skills from Fall 2023-Spring 2024. |  |
| - Engage students in internal and external extracurricular activities that promote literacy. | - SC - Teachers - Students - HoSs | - Circulars - Budget - Venue | - Sept. 2023-June 2024 | - All students are actively engaged in reading and writing. - In MAP Reading interim assessments, at least 61% of Gr.3-4 students show progress in reading level from Spring 2023-Spring 2024. - In NGRT at least 61% of Gr.1-4 students show progress in reading literacy skills from Fall 2023-Spring 2024. |  |
| - Introduce a Literacy Committee comprising subject leaders, teachers, and high achieving students of G9-12 (consistently getting high scores in NGRT, MAP and CAT4 Verbal battery) with the following objectives: - Promote literacy awareness - Increase literacy rates - Organize literacy events - Measure and track progress of literacy goals - Support research into effective literacy strategies and stay updated on best practices. | - SC - Teachers - Students - Activities Coordinator | - Meeting schedule - Progress tracking documents - Events calendar - Data from assessments | - January 2024 – June 2024 | - Students’ reading scores in NGRT and MAP improve by 5-10%. - At least two research projects or studies related to literacy improvement are initiated annually. - At least two new literacy strategies are added into the curriculum per year. - At least 70% of committee members attend literacy conferences, workshops, or training sessions annually. - At least 3 literacy awareness campaigns or workshops are conducted annually for parents and students. |  |

| Key Area 3: Ensure that teachers in the upper phases provide regular opportunities for students to research using technology and that they evaluate information from multiple sources |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key Actions | Lead Person | Resources/ Cost | Timeline | Success Criteria | Progress |
| - Create a research framework to set clear objectives and expectations to integrate research skills in the curriculum. | - SCs - Teachers | - Research framework and guidelines | - Sep 2023-June 2024 | - All teachers develop competence in integrating research skills in their planning. |  |
| - Develop and provide professional development training for teachers on research methodologies using technology: - Investigative techniques - Data analysis - Information literacy | - SCs - Teachers | - PD Time - PD Schedule - Learn online | - Aug.2023-June 2024 | - All teachers integrate research skills in their planning. - Most students develop independent learning and research skills. |  |
| - Establish horizontal committee that includes teachers from different content areas to: - Collaborate in planning interdisciplinary activities and projects related to research skill development. - Share best practices on successful teaching strategies that promote research. | - SCs - Teachers | - Meeting time - Meeting minutes | - Sept.2023-June 2024 | - At least 1 interdisciplinary activity/project is planned and implemented per semester. |  |
| - Build on inquiry-based learning and performance-based learning that promote research skills that aim at augmenting knowledge from multiple sources. | - SCs - Teachers | - Lesson plans - Students’ work | - Sep.2023-June 2024 | - In phase 2, at least 75% of students meet the curriculum expectations in MAP Spring 2024 and at least 50% of students exceed the curriculum expectations in MAP Spring 2024. - In phases 3 and 4, at least 75% of students meet the curriculum expectations in MAP Spring 2024 and at least 61% of students exceed the curriculum expectations in MAP Spring 2024. |  |
| - Utilize the available space from discontinuing the Computer Lab by dedicating it to a new science lab to create more opportunities for students to enquire, investigate and apply research | - Principal - Facilities Manager - Science Coordinator | - Budget resources for science equipment - Timetable sessions | - January 2023 | - Dedicated sessions in the timetable available for lab - Students are utilizing the lab to conduct investigative experiments. - Students are producing high quality lab reports |  |

| Key Area 4: Create appropriate systems of feedback on students’ written work and include next steps to improve their learning. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Key Actions | Lead Person | Resources/ Cost | Timeline | Success Criteria | Progress |
| - Provide professional development training for teachers to: - Develop a common and clear understanding of what effective feedback is by determining the following: - Purpose of feedback - Role of goal setting - Role of teachers - Role of student - Use the feedback framework to engage students in the process of receiving and interpreting feedback by using: - Well-designed rubrics - Conferring protocol - Active retrieval practices (self-reflection and peer-reflection) | - SCs - Teachers - Students | - PD Time - PD Schedule - Rubrics - Running Records - Student Profile - Feedback framework | - Aug .2023-June 2024 | - All students are actively engaged in their learning. - At least 80 % of students demonstrate independent learning skills. - At least 61% of students show progress from MAP Spring 2023 to MAP Spring 2024 |  |